## PoC - Blogger
.NetForte: Case Study - Blogger Application Development
Task # | Description | Resource Name | Status | Start Date | End Date | Comments
Project Setup And Architecture
1 | Define the application architecture and database schema. | Everyone | Completed | 2023-09-25 | 2023-10-06
2 | Flowchart diagrams/ UI Layouts | Prabu E | Completed | 2023-10-04 | 2023-10-06
UI Design
3 | Design the application's layout, including the homepage, user profiles, and blog post pages | Prabu E | Completed
4 | Define a consistent color scheme, typography, and visual style for the application. | Everyone | In Progress
User Management
5 | Implement user registration and authentication.
6 | Create user profiles with basic information.
Blog Post Management
7 | Develop a feature for users to create, edit, and delete blog posts.
8 | Implement image upload for blog posts.
Commenting System
9 | Create a commenting system for blog posts
Blog Search and Filters
10 | Implement search functionality to find blog posts
11 | Add filters based on categories, date, and popularity
Notifications
12 | Implement email notifications for comments
Deployment
13 | Deploy the application into Azure Database WebAPI Web App | Prabu E | Yet to start

## App Modules
Asp.Net Core Web App (Razor Pages)
Asp.Net Core Web API
SQL Server